## Sheet1
Tasks and Assignment Breakdown
| Group: | Team TBD
| Team Members (and initials): | JT Kashuba (JK), Noah Kruss (NK), Logan Levitre (LL), Zeke Petersen (ZP), River Veek (RV)
| Date this was last updated: | 2021-03-10
| Last updated by (whom): | ZP
Grouping | Task or Milestone (with an objectively verifiable completion) | Status | Assigned to (whom) | Date Assigned | Anticipated Time (hours) | Date Due | Date Completed | Completed by (whom) | Time Spent (hours) | Confirmed Completed by (whom) | Date Confirmed Complete | Notes
Week 1 (Framework)
| SRS/SDS/Project Plan (3 page) | Completed | ZP, NK, RV | 2021-02-12 | 6 | 2021-02-14 | 2021-02-13 | ZP, NK, RV | 3.0, 3.0, 1.0 | NK | 2021-02-13
| SRS/SDS/Project Plan (Full) | Completed | ZP, RV, NK | 2021-02-15 | 10 | 2021-02-18 | 2021-02-17 | ZP, RV, NK | 5, 2.5, 2.5 | NK | 2021-02-17
| Establish Docker container creation code (Flask framework for web app) | Completed | JK | 2021-02-12 | 5 | 2021-02-19 | 2021-02-15 | JK | 3 | ZP | 2021-02-16
| Design web interface v1 (fields for UI, basic visualization) | Completed | LL | 2021-02-12 | 8 | 2021-02-19 | 2021-02-15 | LL | 5 | ZP | 2021-02-16
| Set up pickling (store dummy data) | Completed | RV | 2021-02-12 | 5 | 2021-02-19 | 2021-02-17 | RV, ZP | 0.25, 0.25
| Create webhook for discord server | Completed | JK | 2021-02-12 | 1 | 2021-02-19 | 2021-02-18 | JK | 2 | JK | 2021-02-18
| Create Presentation Slides | Completed | JK, NK | 2021-02-17 | 2 | 2021-02-18 | 2021-02-18 | JK, NK | 2.0, 2.0 | JK | 2021-02-18
Week 2 (Integration/ Logic)
| Create CIS_Major Degree object | Completed | JK, RV | 2021-02-21 | 1 | 2021-02-24 | 2021-02-22 | JK, RV | 2.5, 2.0 | RV | 2021-02-22
| Create base Student, Degree, and Course classes | Completed | NK, ZP | 2021-02-15 | 5 | 2/29/21 | 2021-02-25 | NK | 4.0, 1.0 | LL | 2021-02-27
| Create web interface v2 -- Bootstrap | Completed | ZP, LL | 2021-02-21 | 8 | 2/29/21 | 2021-02-25 | ZP, LL | 6,4 | ZP | 2021-02-27
| Create first draft of User Instructions / Installation Instructions | Completed | RV | 2021-02-21 | 4 | 2/29/21 | 2021-02-25 | RV | 3 | JK, ZP | 2021-02-27
| First Draft of logic for creating degree plan forecast | Completed | JK, NK | 2021-02-21 | 8 | 2/29/21 | 2021-02-25 | JK, NK | 0.5, 4.0 | LL | 2021-02-27
| Test class object methods (including pickle file save/load) | Completed | RV, NK | 2021-02-21 | 1 | 2021-02-27 | 2021-03-07 | RV, NK | 6.75, 2.5 | ZP | 2021-03-08
| Update CIS_degree.py to show possible courses available during Summer term | Completed | JK | 2021-02-24 | 1 | 2021-02-28 | 2021-02-24 | JK | 0.5 | JK | 2021-02-24
| Create Gen_Ed Degree object | Completed | JK | 2021-02-24 | 2 | 2021-02-28 | 2021-02-24 | JK | 2 | JK | 2021-02-24
| Fix pre-requisites for courses in the CIS_degree object | Completed | JK | 2021-02-25 | 1 | 2021-02-27 | 2021-02-25 | JK | 1.5 | LL | 2021-02-27
Week 3 (Logic/ More Features)
| Connect to flask to populate dropdowns | Completed | ZP, LL | 2021-02-23 | 5 | 2021-02-27 | 2021-02-27 | ZP, LL | 3.5, 3 | ZP | 2021-02-28
| Function to return all pickle file names | Completed | RV | 2021-02-27 | 1 | 2021-05-03 | 2021-02-27 | RV | 0.5 | ZP | 2021-03-02
| Send table data back to flask | Completed | ZP, LL, JK | 2021-02-27 | 4 | 2/29/2021 | 2021-03-01 | ZP, LL, JK | 0.5, 8.0, 3.0 | ZP | 2021-03-04
| Finalize elective, pre-req and term logic | Completed | NK | 2021-02-27 | 4 | 2021-03-02 | 2021-02-27 | NK | 2.5 | ZP | 2021-03-04
| Adding course difficulty logic | Incompleted | NK, RV | 2021-02-27 | 5 | N/A | N/A | N/A | N/A | N/A | N/A | Postponing indefinitely.
| Create architecture diagram | Completed | ZP | 2021-02-27 | 0.5 | 2/29/2021 | 2021-02-27 | ZP | 0.5 | JK | 2021-03-01
| Parse forecast dict into list for HTML display | Completed | JK | 2021-03-02 | 4 | 2021-03-05 | 2021-03-03 | JK | 4.5 | ZP | 2021-03-04
| Finish app.py | Completed | ZP | 2021-03-02 | 3 | 2021-03-04 | 2021-03-04 | ZP | 8.5 | JK | 2021-03-07
Week 4 (Cleanup/ check compliance)
| Update SRS 3.1/3.2 | Completed | RV | 2021-03-06 | 2 | 2021-03-09 | 2021-03-06 | RV | 1 | JK | 2021-03-10
| Replace Logic module with the object and planning modules in SDS | Completed | NK | 2021-03-06 | 3 | 2021-03-09 | 2021-03-06 | NK | 1.5 | ZP | 2021-03-08
| Add flask module to SDS | Completed | ZP | 2021-03-06 | 1 | 2021-03-09 | 2021-03-07 | ZP | 1 | LL | 2021-03-08
| Update interface module in SDS | Completed | ZP | 2021-03-06 | 1 | 2021-03-09 | 2021-03-07 | ZP | 1 | LL | 2021-03-08
| Rewrite/update SDS Sections 2 and 3 | Completed | ZP | 2021-03-06 | 1 | 2021-03-09 | 2021-03-07 | ZP | 0.5 | LL | 2021-03-08
| Finalize CIS_degree.py & Gen_Ed.py | Completed | JK | 2021-03-06 | 0.5 | 2002-03-09 | 2021-03-07 | JK | 1 | LL | 2021-03-09
| Update README | Completed | JK | 2021-03-06 | 1 | 2021-03-09 | 2021-03-07 | JK | 2.5 | ZP | 2021-03-10
| Updated SRS and SDS | Completed | JK, NK, LL, ZP, RV | 2021-03-06 | 2 | 2021-03-11 | 2021-03-07 | JK, NK, LL, ZP, RV | 1.5, 1.0, 1.0, 2.0, 1.5 | ZP | 2021-03-09
| Update User Instructions, Install Instructions | Completed | RV | 2021-03-04 | 1 | 2021-03-09 | 2021-03-06 | RV | 1.7 | ZP | 2021-03-09
| Finalize Programmer Documentation | Completed | JK, NK, LL, ZP, RV | 2021-03-06 | 2 | 2021-03-09 | 2021-03-10 | JK, NK, LL, ZP, RV | 2.0,2.0,1.0,2.0,1.5 | ZP | 2021-03-10
| Create Presentation Outline | Completed | RV | 2021-03-07 | 1 | 2021-03-10 | 2021-03-08 | RV | 1 | ZP | 2021-03-08
| SDS/SRS Checkoff - JT | Completed | JK | 2021-03-08 | 0.5 | 2021-03-09 | 2021-03-09 | JK | 0.5 | ZP | 2021-03-09
| SDS/SRS Checkoff - Noah | Completed | NK | 2021-03-08 | 0.5 | 2021-03-09 | 2021-03-08 | NK | 0.5 | ZP | 2021-03-09
| SDS/SRS Checkoff - Logan | Completed | LL | 2021-03-08 | 0.5 | 2021-03-09 | 2021-03-08 | LL | 0.5 | ZP | 2021-03-09
| SDS/SRS Checkoff - Zeke | Completed | ZP | 2021-03-08 | 0.5 | 2021-03-09 | 2021-03-08 | ZP | 0.5 | ZP | 2021-03-09
| SDS/SRS Checkoff - River | Completed | RV | 2021-03-08 | 0.5 | 2021-03-09 | 2021-03-09 | RV | 1.5 | ZP | 2021-03-09
Project Planning
| Establish Discord server, shared repo, tracking documents | Completed | all staff | 2021-02-12 | 2 | N/A | 2021-02-12 | all staff | 2 | all staff | 2021-02-12
| Establish regular meeting schedule | Completed | all staff | N/A | N/A | N/A | 2021-02-13 | all staff | N/A | all staff | 2021-02-12 | Wednesdays at 4pm
| Initial meeting | Completed | all staff | 2021-02-12 | 1 | 2021-02-12 | 2021-02-12 | all staff | 1.5 | all staff | 2021-02-12
| Meeting to discuss architecture | Completed | all staff | 2021-02-15 | 1 | 2021-02-15 | 2021-02-15 | all staff | 1 | all staff | 2021-02-15
| Weekly Meeting 1 | Completed | all staff | 2021-02-17 | 1 | 2021-02-17 | 2021-02-17 | all staff | 1 | all staff | 2021-02-17
| Presentation Tech Rehearsal and Group Meeting | Completed | all staff | 2021-02-18 | 1 | 2021-02-18 | 2021-02-18 | all staff | 1 | all staff | 2021-02-18
| Group Meeting | Completed | all staff | 2021-02-21 | 0.5 | 2021-02-21 | 2021-02-21 | all staff | 0.5 | JK | 2021-02-21
| Progress Meeting #1 w/ Prof Flores | Completed | all staff | 2021-02-23 | 0.33 | 2021-02-23 | 2021-02-23 | all staff | 0.3 | JK | 2021-02-23
| Impromptu Group Meeting | Completed | JK, NK, LL, RV | 2021-02-23 | 0.5 | 2021-02-23 | 2021-02-23 | JK, NK, LL, RV | 1.5, 1.5, 0.5, 0.5 | JK | 2021-02-23 | Discussed Project Plan in regards to scope, JK and NK brainstormed how to handle electives
| Weekly Meeting 2 | Completed | all staff | 2021-02-24 | 1 | 2021-02-24 | 2021-02-24 | all staff | 1 | all staff | 2021-02-24
| Weekend Meeting | Completed | all staff | 2021-02-27 | 1 | 2021-02-27 | 2021-02-27 | all staff | 1 | all staff | 2021-02-27
| Impromptu Front-End Meeting | Completed | JK, LL, ZP | 2021-03-01 | 0.5 | 2021-03-01 | 2021-03-01 | JK, LL, ZP | 1 | JK, LL, ZP | 2021-03-01
| Progress Meeting #2 w/ Prof Flores | Completed | all staff | 2021-03-02 | 0.3 | 2021-03-02 | 2021-03-02 | all staff | 0.3 | JK | 2021-03-02
| Weekly Meeting 3 | Completed | all staff | 2021-03-03 | 1 | 2021-03-03 | 2021-03-03 | all staff | 1 | JK | 2021-03-03
| Impromptu Meeting | Completed | JK, LL, ZP, RV | 2021-03-04 | 0.5 | 2021-03-04 | 2021-03-04 | JK, LL, ZP, RV | 0.5 | JK | 2021-03-04
| Weekend Meeting | Completed | all staff | 2021-03-06 | 0.5 | 2021-03-06 | 2021-03-06 | all staff | 0.75 | JK | 2021-03-06
| Impromptu Meeting | Completed | JK, NK, RV | 2021-03-07 | 1 | 2021-03-07 | 2021-03-07 | JK, NK, RV | 1.25 | JK | 2021-03-07
| Presentation Meeting | Completed | all staff | 2021-03-08 | 1 | 2021-03-08 | 2021-03-08 | all staff | 1 | JK | 2021-03-08
| Final Presentation Tech Rehearsal | Completed | all staff | 2021-03-10 | 0.5 | 2021-03-10 | 2021-03-10 | all staff | 0.75 | JK | 2021-03-10
| Final Group Meeting | Completed | all staff | 2021-03-10 | 1 | 2021-03-10 | 2021-03-10 | all staff | 1 | JK | 2021-03-10